CARRIER CLIENT ONBOARDING — WORKFLOW PLAYBOOK

Carrier-in-a-Box — the repeatable system  ·  Spark Network Midwest | 614 Management

One defined path every carrier client walks, intake to ongoing management. Each task has an owner, a 'done' definition, and a template. Designed so credit-only and funding-only clients plug in as their own templates.

How this works

Phases run in order. Each phase starts when the prior one's tasks are done. Adding a client spawns this whole checklist; nothing is decided from scratch.

Owners are roles, not names. Assign Coordinator, CFO/Finance, Setup Specialist, or Client as you build the team — so work delegates cleanly.

Templates are fixed assets. Every task points to a standard document or system so output is identical each time.

The Carrier Onboarding Phases

PHASE 1: Intake & Qualification

Starts when: A lead is captured (referral, package inquiry, JV funnel).

| Task | Owner | Output / Done when | Template |
| --- | --- | --- | --- |
| Capture lead + intake form | Coordinator | Intake form complete; client goals + budget known | Intake form |
| Qualify & recommend tier | CFO/Finance | Starter/Growth/Empire selected | Package sheet |
| Send proposal + agreement | Coordinator | Proposal + Management Agreement sent | Mgmt Agreement |

PHASE 2: Agreement & Payment

Starts when: Client accepts the proposal.

| Task | Owner | Output / Done when | Template |
| --- | --- | --- | --- |
| Execute Management & Services Agreement | Client / CFO | Signed agreement on file | Services Agreement |
| Collect deposit / setup fee | CFO/Finance | Payment received; holdback for hard costs set | Invoice + Stripe |
| Open client file + spawn checklist | Coordinator | Client record created in portal | Portal |

PHASE 3: Entity Formation

Starts when: Agreement signed + deposit paid.

| Task | Owner | Output / Done when | Template |
| --- | --- | --- | --- |
| Form LLC/Corp + EIN | Setup Specialist | Articles filed, EIN issued | Formation packet |
| Operating Agreement / bylaws | Setup Specialist | OA executed | OA template |
| Statutory agent + PPOB set | Coordinator | 700 Taylor Ave (or client address) on file | Address agreement |

PHASE 4: Authority & Compliance

Starts when: EIN issued.

| Task | Owner | Output / Done when | Template |
| --- | --- | --- | --- |
| USDOT + MC authority (FMCSA URS) | Setup Specialist | USDOT/MC numbers issued | Authority checklist |
| BOC-3, UCR, IRP/IFTA | Setup Specialist | Filings confirmed | Compliance checklist |
| Drug & alcohol consortium enroll | Coordinator | Enrollment confirmed | Consortium form |

PHASE 5: Insurance

Starts when: Authority pending (insurance gates activation).

| Task | Owner | Output / Done when | Template |
| --- | --- | --- | --- |
| Bind commercial auto + cargo | Client / Setup | COI issued; BMC-91 filed | Insurance checklist |
| Physical address for inspections | Coordinator | Inspectable location confirmed | Office plan |

PHASE 6: Banking & Systems

Starts when: Entity + EIN ready.

| Task | Owner | Output / Done when | Template |
| --- | --- | --- | --- |
| Open operating + reserve accounts | CFO/Finance | Accounts open; signers set | Banking checklist |
| Stand up portal / ledger + driver upload | Setup Specialist | Portal live for this client | Portal template |
| Connect software stack (Claude/Vercel/Supabase/GitHub) | Setup Specialist | Systems running; billed to company | Systems list |

PHASE 7: Business Credit & Funding

Starts when: Banking open.

| Task | Owner | Output / Done when | Template |
| --- | --- | --- | --- |
| D-U-N-S + net-30 tradeline ladder | CFO/Finance | D-U-N-S issued; tradelines reporting | Credit-build SOP |
| Funding readiness + lender packaging | CFO/Finance | Funding package assembled | Funding template |

PHASE 8: Launch

Starts when: Authority active + insurance bound + truck ready.

| Task | Owner | Output / Done when | Template |
| --- | --- | --- | --- |
| Dispatch + factoring setup (Bluegrass-style) | Setup Specialist | Dispatch live; factoring approved | Dispatch SOP |
| Driver onboarding + 1099 + settlement setup | CFO/Finance | Driver agreement signed; pay structure set | Driver 1099 |
| First load booked + tracked | Coordinator | First load moving | Load SOP |

PHASE 9: Ongoing Management

Starts when: Operation running.

| Task | Owner | Output / Done when | Template |
| --- | --- | --- | --- |
| Weekly settlement + waterfall | CFO/Finance | Weekly P&L + payouts issued | Waterfall SOP |
| Monthly CFO/COO retainer billed | CFO/Finance | Invoice sent per company | Retainer invoice |
| Compliance calendar upkeep | Coordinator | Filings current | Compliance calendar |

Roles (assign as the team grows)

Coordinator — intake, client file, scheduling, communication, compliance calendar.

CFO/Finance — agreements, payments, banking, credit, funding, settlements, billing.

Setup Specialist — formation, authority, insurance coordination, systems, dispatch setup.

Client — signs, pays, provides documents, binds insurance in their name.

Plug-in service lines (same structure, own template)

Credit-only client: Phases 1–2 + Phase 7. Funding-only client: Phases 1–2 + funding tasks. Each reuses the intake/agreement/payment front end, then runs only its relevant phases — so one system scales across all SPARK services.

This playbook is the spec for the portal workflow (Clients & Workflow tab). Build for a team from the start — every task is assignable and trackable.